## Sheet
Phase | Task | Deliverable | My Edits
Phase 0: Preparation | Audit existing content; extract non‑profit vs. for‑profit messaging; identify missing pages (2030 Vision, Finafas, Impact by Numbers) | Content inventory + UX issue log | Add missing elements: “Our 2030 Vision/Mission”, “Finafas Partnership”, “Impact by the Numbers”. UI 2 broken images
| Set up staging (Next.js + Tailwind); install headless CMS (Sanity/Contentful) | Staging repo + CMS schema draft
Phase 1: Content | Rewrite homepage hero with dual focus; add impact stat counter (38,790+ beneficiaries) | Hero copy + stats module | Hero text: “We turn mindset into movement – empowering women & youth through green, tech‑oriented, and inclusive business development.”
| Create program cards based on actual pillars (not placeholder names) | Program descriptions + icons | Five pillars: LEE Incubators, LEE Academy, LEE Business Clinic, LEE Humanitarian Aid, LEE Digital Media Hub - same as company profile
| Write podcast episode page template; include guest bio, transcript, audio player, related programs CTA | Podcast template copy | A small icon or label showing which UN Sustainable Development Goal(s) the episode topic supports. For example, For an episode about women-led agritech startups → badges for SDG 5 (Gender Equality) and SDG 8 (Decent Work) and SDG 13 (Climate Action).
| Draft Impact section: map beneficiaries by country; use real success stories from track record | Impact map + 2 case studies | Use “Akroum Dairy social & solidarity project” or “Mounet Setti” as case studies. Display $1,060,000 seed fund and 2,365 startups incubated could use the written success stories
| Create Community & Events section; add donor/partner logo wall | Event listing + signup form | Add marquee of logos: ILO, UNDP, World Bank, USAID, EU, Canada Embassy, Netherlands Embassy, etc.
| Write “Join the Movement” CTA blocks (volunteering, training, partnership) | 3 CTA modules
| Develop teaser for Finafas financial well‑being platform (your co‑representation) | New program teaser copy | Finafas teaser: “Launching 2026 – Hybrid coaching for financial empowerment.”
| Finalize all content in Google Doc; review tone against company profile keywords | Final content pack | Tone must include: resilient, green economy, women innovators, post‑conflict, mindset into movement, decent work, SDGs
Phase 2: Design | Design system: primary palette (green + gold); add secondary non‑profit palette | Style guide (Figma) | Secondary palette to distinguish humanitarian aid from for‑profit incubation
| Homepage layout: hero → 2030 Vision ribbon → impact stats → programs → podcast → community → CTAs | High-fidelity homepage mockup | Insert “Our 2030 Vision” ribbon with exact text: “To be the leading catalyst for a resilient, green economy across MENA & Africa, powered by women innovators”
| Program detail page template; include eligibility, apply button, testimonial | Program page mockup | Add “Funded by” section (dynamic list of donors per program from track record)
| Podcast archive redesign: filter by season, guest type, country | Podcast archive mockup | Add “Related Track Record Project” link (e.g., agritech episode links to Akroum Dairy project)
| Impact page design: interactive map of MENA countries | Impact page design | Two tabs: “For‑profit impact” (startups incubated, MSMEs accelerated, seed fund) and “Non‑profit impact” (meals distributed, PSS sessions, CFW workers). Use numbers from profile page 2
| Mobile responsive versions of all key pages | Mobile mockups | No change
| Design “Find your track” quiz (3 questions) mapping to real offerings | Quiz UI design | Map to: Incubator / Academy / Business Clinic / Humanitarian Aid / Finafas
| Design review with stakeholders, including non‑profit advisory group | Approved designs | Mandatory review with non‑profit advisors due to dual structure

## Sheet2
Home Page
Current Issue | Suggested Improvement | SEO Keywords | Status/ Notes
5 phrases appears in the first look | Since the content is very rich and wide. All phrases are general too.Only 1 clear Headline appears: Empowering Iivelihoods through technival assistance, capacity building, incubation, and | Empower, solutions, development, impact | 1- Add the social media icons at the end of every landing page especially the homepage
The Mission and Vision section has too much text and repetitive language | Instead, we can divide them so they can visually look like a table of 4 sections, who we are? What we do? Who we serve? Where we work ? |  | 2- At the end, the contact section Add phrase in the blue space: we would love to hear from you
5 minutes Youtube video" ILO promotes entrepreneaurship among lebanese nationals and syrian refugees in lebanon | Instead, I still have few seconds before my bounce rate of my webiste gets high so I prefer to replace with section named: Impact at a Glance. Under it X Countries of operation X% Women reached X youth supported X Programs / Projects delivered X Partners / Donors |  | 3- contact section is missing; Add phone numbers
Add formal View about CEO with Bief about him
4- Mention the exact and updated locations, Lebanon and Eygypt as well.
Our Pillars
Current Issue | Suggested Improvement | SEO Keywords | Status/ Notes
The digital media hub is undercnstruction | Digital Media Hub with subtitle Supporting visibility, communication, and digital solutions for impact-driven initiatives.(along with some infographics)
Only titles of trainings |  | learn more, Programs, capacity building, research, | In this page especially, let a register clik pop up on screen or inder each program.
Our Projects
Current Issue | Suggested Improvement | SEO Keywords | Status/ Notes
there are 9 projects in the subtitles section. Each one of it has the same image in the openeing, same into but different closure and donor name | We shall benefit from these ( pages of the project but only from the Seo part and add more keywords. However to avoid repetition and visual annoyance, a filter that groups them all under the same theme. The filter can have options ()women,youth,donor,year... | Delivered, supported, strengthened,Programs Projects Implementation Delivered Supported Developed Strengthened Improved Market access Livelihoods Economic empowerment MSMEs Cooperatives NGOs Institutions
Get Involved
Current Issue | Suggested Improvement | SEO Keywords | Status/ Notes
Crowd funding landing page is under construction | Add an apply buttom from the website in the careers section
Remove careers that are closed
Reports
Current Issue | Suggested Improvement | SEO Keywords | Status/ Notes
Reports cant be downloaded
Blogs
Current Issue | Suggested Improvement | SEO Keywords | Status/ Notes
The Landing page nder construction |  | How to, guides, improve, build, Training Tutorial Tutorials Explain / Explaining Improve / Improving Build Develop Technique Methods That works
Contact
Current Issue | Suggested Improvement | SEO Keywords | Status/ Notes
| Add a pop up whatsapp icon | contact, work with us, partnerships, opportunities, careers, consultants, trainers, collaboration, intern
Update location and on google maps
Update the social media icons like youtube and X